## Slide 1
Project Planning Example
July 29th, 2013

## Slide 2: Project Planning – Five Questions
  WHY – Purpose of the project
  WHAT – Objectives/outcomes of the project
  HOW – How will this project be accomplished. Break project down into sub-activities and task
  WHO – Person responsible for sub-activity and each task
  WHEN – Date each task should be completed to stay on schedule
It is essential to answer these five questions about large and/or complex projects, especially ones that are prioritized as “Selectively Invest”

## Slide 3: Tactical Team Initiative
    WHY? – Purpose of the project
  Tactical Team is designed to Create Fanatical Customer Service Through In-Store Training. It provides ongoing training to hourly employees (Box office, servers, runners, bartenders, BOH).
  2. WHAT? – What will be accomplished (objectives / outcomes)?
  Consistency across the concept (By Corporate Values)
  Increase recipe knowledge
  Increase customer service through improved greet, menu knowledge, best practice
  Results: increase Per Person Average (PPA), increase tip %, reduce turnover, reduce red light %, increase profitability through more efficient and knowledgeable execution
“W W H W W”

## Slide 4: Tactical Team Framing (HOW)
Tactical Team
Greet
Raving Fans
Core Values
Selling Techniques
Menu/Recipe Knowledge
Assessments
On the Job Training
Guiding Principles Training
Identify opportunities to improve menu knowledge
Set evaluation standards that hold staff accountable
Create online assessment
Deploy assessments 2 weeks prior to Tactical Team
Identify classification criteria
Focus on measurable results
Use recipe Cards
Train side-by-side with employee to reinforce techniques
Ensure the classroom work is interactive
Teach adjectives that describe food
Practice selling food in preshift
Meet & Greet
Develop Food Tasting program
Identify techniques to promote specials
Focus on recipe adherence
Benefit Card used by every employee
Explain the foundations of success
Promise to Customers
Promise to Employees
Develop a focus on cleanliness
Welcome every customer with a smile (10’ Rule)
Staffing boards
Increase BOH attention to detail. Great food
Customer Service

## Slide 5: Tactical Team Task List (WHO/WHEN):
Task | Champion | Team | When | % Complete
Focus on Menu/Recipe Knowledge |  |  |  | 
Assessments |  |  |  | 
Identify opportunities to improve menu knowledge | DH | CG, AM’s,GM’s | 5/15/2013 | 50%
Set evaluations standards that hold staff accountable | DH | CG, AM’s | 8/1/2013 | 70%
Create online assessments | DH | CG, MM | 6/17/2013 | 25%
Deploy assessments 2 weeks prior to Tactical Team | DH | AM’s, GM’s | 6/10/2013 | 90%
Classroom & On the Job Training |  |  |  | 
Identify classification criteria | DH | CG, AM’s,GM’s | 5/1/2013 | 99%
Focus on Measurable results | DH | TC, CG | 6/1/13 | 50%
Use of recipe cards | DH | TK | 5/15/2013 | 35%
Train side-by-side with employees to reinforce techniques | DH | Tactical Team | 6/26/2013 | 0%
Ensure the classroom is interactive | DH | Training Mgrs | 8/1/2013 | 50%
Develop Selling Techniques |  |  |  | 
Greet |  |  |  | 
Implement Meet and Greet | DH | AM,GM | 5/31/2013 | 65%
Teach Adjectives that describe food | DH | Training Mgrs | 6/26/2013 | 25%
Practice selling food in preshift | DH | GM, Unit Mgrs | Daily | 10%
Raving Fans |  |  |  | 
Develop Food Tasting program | CG | DH, AM | 7/1/2013 | 0%
Identify techniques to promote specials | CG | DH,TK,AM,GM | 7/15/2013 | 25%
Focus on recipe adherence | CG | TK | Daily | 50%
Notes: 5

## Slide 6: 2013 Tactical Team Roadmap
 | Q2 2013 | Q3 2013
Focus on Menu: | Assessments: Identify opportunities to improve menu knowledge (CG, AMs, GMs) Create online assessments (CG, MM) Deploy assessments 2 weeks prior to Tactical Team (AMs, GMs) Classroom & On the Job Training: Identify classification criteria (CG, AMs, GMs) Use of recipe cards (TK) Focus on Measurable results (TC, CG) Train side-by-side with employees to reinforce techniques (Tactical Team) | Assessments: Set evaluations standards that hold staff accountable (CG, AM’s) Classroom & On the Job Training: Ensure the classroom is interactive(Training Mgrs)
Develop Selling Techniques: | Greet: Implement Meet and Greet (AMs, GMs) Teach Adjectives that describe food (Training Mgrs) Practice selling food in preshift (GMs, Unit Mgrs) Raving Fans: Focus on recipe adherence (TK) | Greet: Practice selling food in preshift (GMs, Unit Mgrs) Raving Fans: Focus on recipe adherence (TK) Develop food tasting program (DH, AMs) Identify techniques to promote specials (DH,TK,AMs,GMs)