## Slide 1: driversselect Recon Q1 2x2
WIG: Produce 50+ Cars per Week
Introducing New Processes
Implement Internal PDR
Ramon 100% Presence and Engaged (RM)
Hire 4 Techs
(Total 9)
(RM)
Hire Asst Recon Mgr (RM)
Drive Daily huddles with clear Production Commitments (RM)
Tech Training Program
Hand off Recon Cust Care to Sullins
Hire QA Mgr
Stagen Advanced Execution
(RM)
Ensure recon operates to the 3 key principles (RM)
Meet sullins bobbie weekly to agree small improvement actions

## Slide 2: driversselect Recon Q1 2x2
WIG: Produce 50+ Cars per Week
Selectively Invest:
Hire 4 Techs by close of QTR 1to bring Tech count to 9
Dedicate time daily to source, interview, screen technician candidates (minimum 1.5 hrs. daily)
(2) Recent Tech Hires
  William Johnson
  David Gamez
  -Current tech count is 6 pending the start of Gamez will make it (7) still needing 2 to close the QTR
  Joe Roles Tech interview scheduled for 1/5/15 @ 10am
  Jack Grudtz Tech Interview scheduled for 1/8/15 @ 1330hrs
Selectively Invest:
Hire and Train Asst. Recon Mgr.
Dedicate time daily to source, interview, screen mgr. & technician candidates (minimum 1.5 hrs. daily)
Currently in the offer phase for Jose Enrique Garcia
Drive Daily:
100% Presence & Engaged
Daily shop floor focus follow up 3x daily after morning huddle to identify production constraints and game film opportunities prohibiting the team from achieving their daily commitment
Conduct weekly leadership huddle on Wednesday to discuss way to get recon more productive & efficient. Establish WWW for identified items
End of day recap to ensure the Production Flow board reflects the days work and set up for the next days production and commitments
Drive Daily
Daily Team huddles establish clear Recon Output
Conduct daily huddle at 0915 every morning to discuss production commitments (no longer 20 mins)
Discuss each department’s capacity and capability to achieve commitments focusing on 3 questions 1) did you achieve previous days targets 2) What is todays commitment 3) do you foresee any roadblocks
Address issues or concerns outside of daily huddle to stay focused on production expectation
Drive Daily:
Ensure Recon Team is embracing the 3 Key Principles
Drive the importance of Zone / Department ownership to ensure the team is being more efficient and focused.
Ensure work is dispatched according to the Recon Flow Process 2 UCI per tech per day / Mech Parts dispatched by recon flow capacity
End of day recap to ensure the Production Flow board reflects the days work and set up for the next days production and commitments