## Structured Meeting
Meeting | Frequency | Purpose | Attendees
Leadership Team | Weekly | Communicate decisions from NLT Review and Adjust 30, 60, 90 day plan Review cultural orientation of our teams and discuss improvements Review cross team dependencies | Ryan Chuck Mauricio Vince Uzma Kevin Adam
Data Warehouse Team Sync | 2x per month | Review and Adjust 30, 60, 90 day plan Review / discuss / alter workload for Phase 1 Data Warehouse Review / discuss / alter progress on Data Warehouse Roadmap | Kevin Stacie
Lunch with Ryan | 2x per month | Facetime with individual contributors Hear feedback without leaders present Discuss needs of the team and discuss ideas | Rotate 8-10 per session
Monthly Skip-Level with Team Leaders | 1x per month per leader | Personal Check- In Report impacts of overall 30, 60, 90 day plan Career Development Coaching and Mentoring Discuss the pulse of the team and discuss adjustments | All leaders the report to my direct reports
Project Leadership Stand-up | 1x per day | Project status Review and adjust project allocations Discuss hot issues if any Resolve cross project dependencies or delegate Project release dates | All P&T CIO direct reports and their direct reports
Infrastructure Team Sync | 2x per month | Monitor Issues, Code Reds, systems health Discuss project issues if any Review release dates Culture issues if any | Chuck Jana
Development Team Sync | 2x per month | Monitor Development Projects Monitor Support and Code Red issues Technology ratification Cross Program Dependencies Teaming / Culture gauge | Mauricio Uzma Vince Aaron Boat
Mentoring | 1x per month per leader | Coaching and Mentoring for Aaron (Rising Star) | Aaron
1 on 1's with direct reports | 1x per week | Personal Check in Personal Development / Coaching Information Exchange Review commitments on 30, 60, 90 day plan | All Direct Reports

## Structured Meeting Map
| Weekly Team Rhythms | Weekly 1 : 1 with Key Staff | Initiative Rhythms
Objectives & Issues | Team Performance Project reveiws Workload allocation and adjustment Cross project dependendancy Choose information, issues, executive rhythm, other initiatives Post Mortem's | Personal Check In 30, 60, 90 Day review and adjust Coaching and mentoring Choose information, issues, executive rhythm, other initiatives | Adjust and renegotiate commitments Debate and resolve technical implemenation details Debate and resolve requirements / UX issues Demonstrations Post Portem's
Tools & Practices | Dynamic Agenda (TFS/ Rally) 30, 60, 90 day plan Productive Conflict Effective Meetings TFS Metrics Project Scorecard Org and Team Visions (occasionally) | 30, 60, 90 day plan Team 2x2 Personal 2x2 Org and Personal Vision and Purpose Turst Formula | TFS/Rally Dynamic Agenda Effective Meetings Committed Action Council Mode